## Slide 1: Unit IV Project Management: Process, Metrics, Estimations & Scheduling
Prof. M.P.Karnik
madhuri.chavan@viit.ac.in
Department of Computer Engineering
BRACT’S, Vishwakarma Institute of Information Technology, Pune-48
(An Autonomous Institute affiliated to Savitribai Phule Pune University)
(NBA and NAAC accredited, ISO 9001:2015 certified)

## Slide 2: Unit 4
Project Management: Process, Metrics, Estimations & Scheduling
Department of Computer Engineering, VIIT, Pune-48

## Slide 3
Project Management Concepts-The Management Spectrum, People, Product, Process, Project, The W5HH Principle
Metrics in the Process and Project Domains, Software Measurement: size & function oriented metrics(FP & LOC), Metrics for Project and Software Quality
Project Estimation, Observations on Estimation, Project Planning Process, Software Scope and feasibility, Resources: Human Resources, Reusable software, Environmental Resources. Software Project Estimation, Decomposition Techniques
Empirical Estimation Models: Structure, COCOMO II, Estimation of Object-oriented Projects, Specialized Estimation, Software Tools for estimation, Case study
Project Scheduling: Basic Concepts, Defining a Task Set for the Software Project, Defining Task Network, Scheduling with time-line charts, Schedule tracking
Tools: - Microsoft Project, Daily Activity Reporting & Tracking (DART)

## Slide 4: Project Definition
“Unique process consisting of a set of coordinated and controlled activities with start and finish dates, undertaken to achieve an objective conforming to specific requirements, including constraints of time, cost, quality and resources”
A Project is a planned set of activities
A Project has a scope
A Project has time, cost, quality and resource constraints
Project Management
The art of organising, leading, reporting and completing a project through people

## Slide 5: Project Management Concepts
The Management Spectrum
The People
The Product
The Process
The Project

## Slide 6: The Management Spectrum
Effective software project management focuses on these items (in this order)
  The people
    Deals with the cultivation of motivated, highly skilled people
    Consists of the stakeholders, the team leaders, and the software team
  The product
    Product objectives and scope should be established before a project can be planned
  The process
    The software process provides the framework from which a comprehensive plan for software development can be established
  The project
    Planning and controlling a software project is done for one primary reason…it is the only known way to manage complexity
    In a 1998 survey, 26% of software projects failed outright, 46% experienced cost and schedule overruns

## Slide 7: The People: The Stakeholders
Five categories of stakeholders
  Senior managers – define business issues that often have significant influence on the project
  Project (technical) managers – plan, motivate, organize, and control the practitioners who do the work
  Practitioners – deliver the technical skills that are necessary to engineer a product or application
  Customers – specify the requirements for the software to be engineered and other stakeholders who have a peripheral interest in the outcome
  End users – interact with the software once it is released for production use

## Slide 8: The People: Team Leaders (1)
Competent practitioners often fail to make good team leaders; they just don’t have the right people skills
Qualities to look for in a team leader
  Motivation – the ability to encourage technical people to produce to their best ability
  Organization – the ability to mold existing processes (or invent new ones) that will enable the initial concept to be translated into a final product
  Ideas or innovation – the ability to encourage people to create and feel creative even when they must work within bounds established for a particular software product or application

## Slide 9: The People: Team Leaders (2)
Team leaders should use a problem-solving management style
  Concentrate on understanding the problem to be solved
  Manage the flow of ideas
  Let everyone on the team know, by words and actions, that quality counts and that it will not be compromised
Another set of useful leadership qualities
  Problem solving – diagnose, structure a solution, apply lessons learned, remain flexible
  Managerial identity – take charge of the project, have confidence to assume control, have assurance to allow good people to do their jobs
  Achievement – reward initiative, demonstrate that controlled risk taking will not be punished
  Influence and team building – be able to “read” people, understand verbal and nonverbal signals, be able to react to signals, remain under control in high-stress situations

## Slide 10: The People: The Software Team (1)
Seven project factors to consider when structuring a software development team
  The difficulty of the problem to be solved
  The size of the resultant program(s) in source lines of code
  The time that the team will stay together
  The degree to which the problem can be modularized
  The required quality and reliability of the system to be built
  The rigidity of the delivery date
  The degree of sociability (communication) required for the project

## Slide 11: The People: The Software Team (2)
Four organizational paradigms for software development teams
  Closed paradigm – traditional hierarchy of authority; works well when producing software similar to past efforts; members are less likely to be innovative
  Random paradigm – depends on individual initiative of team members; works well for projects requiring innovation or technological breakthrough; members may struggle when orderly performance is required
  Open paradigm – hybrid of the closed and random paradigm; works well for solving complex problems; requires collaboration, communication, and compromise among members
  Synchronous paradigm – organizes team members based on the natural pieces of the problem; members have little communication outside of their subgroups

## Slide 12: The People: The Software Team (3)
Five factors that cause team toxity (i.e., a poisonous team environment)
  A furious work atmosphere
  High frustration that causes friction among team members
  A fragmented or poorly coordinated software process
  An unclear definition of roles on the software team
  Continuous and repeated exposure to failure

## Slide 13: The People: The Software Team (4)
How to avoid these problems
  Give the team access to all information required to do the job
  Do not modify major goals and objectives, once they are defined, unless absolutely necessary
  Give the team as much responsibility for decision making as possible
  Let the team recommend its own process model
  Let the team establish its own mechanisms for accountability (i.e., reviews)
  Establish team-based techniques for feedback and problem solving

## Slide 14: The People: Coordination and Communication Issues
Key characteristics of modern software make projects fail
  scale, uncertainty, interoperability
To better ensure success
  Establish effective methods for coordinating the people who do the work
  Establish methods of formal and information communication among team members

## Slide 15: Group Dynamics
Based on studies published by B. Tuckman in 1965
Updated later in 1977
Describes a four-stage model
  Forming
  Storming
  Norming
  Performing

## Slide 16: Group Dynamics Model
Forming
  Group members rely on safe, patterned behavior and look to the group leader for guidance and direction
  Impressions are gathered and similarities and differences are noted
  Serious topics and feelings are avoided
  To grow, members must surrender the comfort of non-threatening topics and risk the possibility of conflict

## Slide 17: Group Dynamics Model
Storming
  As group members organize for the tasks, conflict predictably results in their personal relations
  Individuals have to bend and mold their feelings to fit the group
  Fear of exposure or fear of failure causes an increased desire for structural clarification and commitment
  Conflicts arise over leadership, structure, power, and authority
  Member behavior may have wide swings based on emerging issues of competition and conflicts.
  Some members remain silent while others attempt to dominate

## Slide 18: Group Dynamics Model (continued)
Norming
  Members engage in active acknowledgement of all members’ contributions, community building, and solving of group issues
  Members are willing to change their preconceived ideas or opinions based on facts presented by the group
  Leadership is shared, active listening occurs, and isolation dissolved
  Members began to identify with one another, which leads to a level of trust in their personal relations and contributes to cohesion
  Members begin to experience a sense of group belonging

## Slide 19: Group Dynamics Model (continued)
Performing
  The capacity, range, and depth of personal relations in the group expand to true interdependence
  Members can work independently, in subgroups, or altogether with equal ability and success
  The group is most productive, members become self-assuring, and the need for group approval is past
  Genuine problem solving can occur leading towards optimal solutions

## Slide 20: The Process
The generic phases that characterize the software process – definition, development, and support – are applicable to all software.
The problem is to select the process that is appropriate for the software to be engineered by a project team.

## Slide 21: The Process
The linear sequential model
The prototyping model
The RAD(Rapid Application Development) model
The incremental model
The spiral model
The component-based development model
The concurrent development model
The formal methods
The fourth generation techniques model

## Slide 22: The Process
Must decide which model is most appropriate for
the customers
The characteristics of the product
The project environemnt

## Slide 23: The Process
  The project manager must decide which process model is most appropriate based on
    The customers who have requested the product and the people who will do the work
    The characteristics of the product itself
    The project environment in which the software team works
  Once a process model is selected, a preliminary project plan is established based on the process framework activities
  Process decomposition then begins
  The result is a complete plan reflecting the work tasks required to populate the framework activities
  Project planning begins as a merging of the product and the process based on the various framework activities

## Slide 24: The Product
The scope of the software development must be established and bounded
  Context – How does the software to be built fit into a larger system, product, or business context, and what constraints are imposed as a result of the context?
  Information objectives – What customer-visible data objects are produced as output from the software? What data objects are required for input?
  Function and performance – What functions does the software perform to transform input data into output? Are there any special performance characteristics to be addressed?
Software project scope must be unambiguous and understandable at both the managerial and technical levels

## Slide 25: The Product (continued)
Problem decomposition
  Also referred to as partitioning or problem elaboration
  Sits at the core of software requirements analysis
Two major areas of problem decomposition
  The functionality that must be delivered
  The process that will be used to deliver it

## Slide 26: The Project: A Common Sense Approach (1)
Start on the right foot
  Understand the problem; set realistic objectives and expectations; form a good team
Maintain momentum
  Provide incentives to reduce turnover of people; emphasize quality in every task; have senior management stay out of the team’s way
Track progress
  Track the completion of work products; collect software process and project measures; assess progress against expected averages

## Slide 27: The Project: A Common Sense Approach (2)
Make smart decisions
  Keep it simple; use Commercial Off The Shelf (COTS) or existing software before writing new code; follow standard approaches; identify and avoid risks; always allocate more time than you think you need to do complex or risky tasks
Conduct a post mortem analysis
  Track lessons learned for each project; compare planned and actual schedules; collect and analyze software project metrics; get feedback from teams members and customers; record findings in written form.

## Slide 28: The Project: Signs that it is in risk
Software people don't understand their customer's needs
The product scope is poorly defined
Changes are managed poorly
The chosen technology changes
Business needs change (or are poorly defined)
Deadlines are unrealistic
Users are resistant
Sponsorship is lost (or was never properly obtained)
The project team lacks people with appropriate skills
Managers (and practitioners) avoid best practices and lessons learned

## Slide 29: The Project: The W5HH Principle
Why is the system being developed?
  Assesses the validity of business reasons and justifications
What will be done?
  Establishes the task set required for the project
When will it be done?
  Establishes a project schedule
Who is responsible for a function?
  Defines the role and responsibility of each team member
A series of questions that lead to a definition of key project characteristics
and the resultant project plan. Barry Boehm suggests an approach that addresses project objectives, milestones and schedules, responsibilities, management and technical approaches, and requires resources

## Slide 30
Where are they organizationally located?
  Notes the organizational location of team members, customers, and other stakeholders
How will the job be done technically and managerially?
  Establishes the management and technical strategy for the project
How much of each resource is needed?
  Establishes estimates based on the answers to the previous questions

## Slide 31: References
1) www-fusion-magnetique.cea.fr › ppe › TrainingWeekCulham › Introducti...
2) hustina.staff.gunadarma.ac.id › Downloads › files › bab3

## Slide 32
Thank You