## Slide 1: Unit IV Project Management: Process, Metrics, Estimations & Scheduling
Prof. M.P.Karnik
madhuri.chavan@viit.ac.in
Department of Computer Engineering
BRACT’S, Vishwakarma Institute of Information Technology, Pune-48
(An Autonomous Institute affiliated to Savitribai Phule Pune University)
(NBA and NAAC accredited, ISO 9001:2015 certified)

## Slide 2
Project Management Concepts-The Management Spectrum, People, Product, Process, Project, The W5HH Principle
Metrics in the Process and Project Domains, Software Measurement: size & function oriented metrics(FP & LOC), Metrics for Project and Software Quality
Project Estimation, Observations on Estimation, Project Planning Process, Software Scope and feasibility, Resources: Human Resources, Reusable software, Environmental Resources. Software Project Estimation, Decomposition Techniques
Empirical Estimation Models: Structure, COCOMO II, Estimation of Object-oriented Projects, Specialized Estimation, Software Tools for estimation, Case study
Project Scheduling: Basic Concepts, Defining a Task Set for the Software Project, Defining Task Network, Scheduling with time-line charts, Schedule tracking
Tools: - Microsoft Project, Daily Activity Reporting & Tracking (DART)
Department of Computer Engineering, VIIT, Pune-48

## Slide 3: Estimation for Software Projects
Project planning
Scope and feasibility
Project resources
Estimation of project cost and effort
Decomposition techniques
Empirical estimation models
Department of Computer Engineering, VIIT, Pune-48

## Slide 4: Project Planning
Department of Computer Engineering, VIIT, Pune-48

## Slide 5: Software Project Planning
Software project planning includes five major activities
  Estimation, scheduling, risk analysis, quality management planning, and change management planning
Estimation determines how much money, effort, resources, and time it will take to build a specific system or product
The software team first estimates
  The work to be done
  The resources required
  The time that will elapse from start to finish
Then they establish a project schedule that
  Defines tasks and milestones
  Identifies who is responsible for conducting each task
  Specifies the inter-task dependencies
Department of Computer Engineering, VIIT, Pune-48

## Slide 6: Observations on Estimation
Planning requires technical managers and the software team to make an initial commitment
Process and project metrics can provide a historical perspective and valuable input for generation of quantitative estimates
Past experience can help greatly
Estimation carries inherent risk, and this risk leads to uncertainty
The availability of historical information has a strong influence on estimation risk
Department of Computer Engineering, VIIT, Pune-48

## Slide 7: Observations on Estimation (continued)
When software metrics are available from past projects
  Estimates can be made with greater assurance
  Schedules can be established to avoid past difficulties
  Overall risk is reduced
Estimation risk is measured by the degree of uncertainty in the quantitative estimates for cost, schedule, and resources
Nevertheless, a project manager should not become compulsive about estimation
  Plans should be iterative and allow adjustments as time passes and more is made certain
Department of Computer Engineering, VIIT, Pune-48

## Slide 8: Task Set for Project Planning
Establish project scope
Determine feasibility
Analyze risks
Define required resources
  Determine human resources required
  Define reusable software resources
  Identify environmental resources
Estimate cost and effort
  Decompose the problem
  Develop two or more estimates using different approaches
  Reconcile the estimates
Develop a project schedule
  Establish a meaningful task set
  Define a task network
  Use scheduling tools to develop a timeline chart
  Define schedule tracking mechanisms
Department of Computer Engineering, VIIT, Pune-48

## Slide 9: Scope and Feasibility
Department of Computer Engineering, VIIT, Pune-48

## Slide 10: Software Scope
Software scope describes
  The functions and features that are to be delivered to end users
  The data that are input to and output from the system
  The "content" that is presented to users as a consequence of using the software
  The performance, constraints, interfaces, and reliability that bound the system
Scope can be define using two techniques
  A narrative description of software scope is developed after communication with all stakeholders
  A set of use cases is developed by end users
Department of Computer Engineering, VIIT, Pune-48

## Slide 11: Software Scope (continued)
After the scope has been identified, two questions are asked
  Can we build software to meet this scope?
  Is the project feasible?
Department of Computer Engineering, VIIT, Pune-48

## Slide 12: Feasibility
After the scope is resolved, feasibility is addressed
Software feasibility has four dimensions
  Technology – Is the project technically feasible? Is it within the state of the art? Can defects be reduced to a level matching the application's needs?
  Finance – Is it financially feasible? Can development be completed at a cost that the software organization, its client, or the market can afford?
  Time – Will the project's time-to-market beat the competition?
  Resources – Does the software organization have the resources needed to succeed in doing the project?
Another view recommends the following feasibility dimensions: technological,
economical, legal, operational, and schedule issues (TELOS)
Department of Computer Engineering, VIIT, Pune-48

## Slide 13: Project Resources
Department of Computer Engineering, VIIT, Pune-48

## Slide 14: Resource Estimation
Three major categories of software engineering resources
  People
  Development environment
  Reusable software components
    Often neglected during planning but become a principal concern during the construction phase of the software process
Each resource is specified with
  A description of the resource
  A statement of availability
  The time when the resource will be required
  The duration of time that the resource will be applied
Time window
Department of Computer Engineering, VIIT, Pune-48

## Slide 15: Categories of Resources
People
Number required
Skills required
Geographical location
Development Environment
Software tools
Computer hardware
Network resources
Reusable Software Components
Off-the-shelf components
Full-experience components
Partial-experience components
New components
The
Project
Department of Computer Engineering, VIIT, Pune-48

## Slide 16: Human Resources
Planners need to select the number and the kind of people skills needed to complete the project
They need to specify the organizational position and job specialty for each person
The number of people required can be determined only after an estimate of the development effort
Department of Computer Engineering, VIIT, Pune-48

## Slide 17: Development Environment Resources
A software engineering environment (SEE) incorporates hardware, software, and network resources that provide platforms and tools to develop and test software work products
Most software organizations have many projects that require access to the SEE provided by the organization
Planners must identify the time window required for hardware and software and verify that these resources will be available
Department of Computer Engineering, VIIT, Pune-48

## Slide 18: Reusable Software Resources
Off-the-shelf components
  Components are from a third party or were developed for a previous project
  Ready to use; fully validated and documented; virtually no risk
Full-experience components
  Components are similar to the software that needs to be built
  Software team has full experience in the application area of these components
  Modification of components will sustain relatively low risk
Department of Computer Engineering, VIIT, Pune-48

## Slide 19
Partial-experience components
  Components are related somehow to the software that needs to be built but will require substantial modification
  Software team has only limited experience in the application area of these components
  Modifications that are required have a fair degree of risk
New components
  Components must be built from scratch by the software team specifically for the needs of the current project
  Software team has no practical experience in the application area
  Software development of components has a high degree of risk

## Slide 20: Estimation of Project Cost and Effort
Department of Computer Engineering, VIIT, Pune-48

## Slide 21: Factors Affecting Project Estimation
The accuracy of a software project estimate is predicated on
  The degree to which the planner has properly estimated the size (e.g., KLOC) of the product to be built
  The ability to translate the size estimate into human effort, calendar time, and money
  The degree to which the project plan reflects the abilities of the software team
  The stability of both the product requirements and the environment that supports the software engineering effort
Department of Computer Engineering, VIIT, Pune-48

## Slide 22: Project Estimation Options
Options for achieving reliable cost and effort estimates
  Delay estimation until late in the project (we should be able to achieve 100% accurate estimates after the project is complete)
  Base estimates on similar projects that have already been completed
  Use relatively simple decomposition techniques to generate project cost and effort estimates
  Use one or more empirical estimation models for software cost and effort estimation
Option #1 is not practical, but results in good numbers
Option #2 can work reasonably well, but it also relies on other project influences being roughly equivalent
Options #3 and #4 can be done in cycle to cross-check each other
Department of Computer Engineering, VIIT, Pune-48

## Slide 23: Project Estimation Approaches
Decomposition techniques
  These take a "divide and conquer" approach
  Cost and effort estimation are performed in a stepwise fashion by breaking down a project into major functions and related software engineering activities
Empirical estimation models
  Offer a potentially valuable estimation approach if the historical data used to seed the estimate is good
Department of Computer Engineering, VIIT, Pune-48

## Slide 24: Decomposition Techniques
Department of Computer Engineering, VIIT, Pune-48

## Slide 25: Introduction
Before an estimate can be made and decomposition techniques applied, the planner must
  Understand the scope of the software to be built
  Generate an estimate of the software’s size
Then one of two approaches are used
  Problem-based estimation
    Based on either source lines of code or function point estimates
  Process-based estimation
    Based on the effort required to accomplish each task
Department of Computer Engineering, VIIT, Pune-48

## Slide 26: Approaches to Software Sizing
Function point sizing
  Develop estimates of the information domain characteristics
Standard component sizing
  Estimate the number of occurrences of each standard component
  Use historical project data to determine the delivered LOC size per standard component
Change sizing
  Used when changes are being made to existing software
  Estimate the number and type of modifications that must be accomplished
  Types of modifications include reuse, adding code, changing code, and deleting code
  An effort ratio is then used to estimate each type of change and the size of the change
The results of these estimates are used to compute an optimistic (low), a most likely,
and a pessimistic (high) value for software size
Department of Computer Engineering, VIIT, Pune-48

## Slide 27: Problem-Based Estimation
Start with a bounded statement of scope
Decompose the software into problem functions that can each be estimated individually
Compute an LOC or FP value for each function
Derive cost or effort estimates by applying the LOC or FP values to your baseline productivity metrics (e.g., LOC/person-month or FP/person-month)
Combine function estimates to produce an overall estimate for the entire project
Department of Computer Engineering, VIIT, Pune-48

## Slide 28: Problem-Based Estimation (continued)
In general, the LOC/pm and FP/pm metrics should be computed by project domain
  Important factors are team size, application area, and complexity
LOC and FP estimation differ in the level of detail required for decomposition with each value
  For LOC, decomposition of functions is essential and should go into considerable detail (the more detail, the more accurate the estimate)
  For FP, decomposition occurs for the five information domain characteristics and the 14 adjustment factors
    External inputs, external outputs, external inquiries, internal logical files, external interface files
pm = person month
Department of Computer Engineering, VIIT, Pune-48

## Slide 29: Problem-Based Estimation (continued)
For both approaches, the planner uses lessons learned to estimate an optimistic, most likely, and pessimistic size value for each function or count (for each information domain value)
Then the expected size value S is computed as follows: S = (Sopt + 4Sm + Spess)/6
Historical LOC or FP data is then compared to S in order to cross-check it
Department of Computer Engineering, VIIT, Pune-48

## Slide 30: Process-Based Estimation
Identify the set of functions that the software needs to perform as obtained from the project scope
Identify the series of framework activities that need to be performed for each function
Estimate the effort (in person months) that will be required to accomplish each software process activity for each function
Department of Computer Engineering, VIIT, Pune-48

## Slide 31: Process-Based Estimation (continued)
Apply average labor rates (i.e., cost/unit effort) to the effort estimated for each process activity
Compute the total cost and effort for each function and each framework activity
Compare the resulting values to those obtained by way of the LOC and FP estimates
  If both sets of estimates agree, then your numbers are highly reliable
  Otherwise, conduct further investigation and analysis concerning the function and activity breakdown
This is the most commonly used of the two estimation techniques (problem and process)
Department of Computer Engineering, VIIT, Pune-48

## Slide 32: Reconciling Estimates
The results gathered from the various estimation techniques must be reconciled to produce a single estimate of effort, project duration, and cost
If widely different estimates occur, investigate the following causes
  The scope of the project is not adequately understood or has been misinterpreted by the planner
  Productivity data used for problem-based estimation techniques is inappropriate for the application, obsolete (i.e., outdated for the current organization), or has been misapplied
The planner must determine the cause of divergence and then reconcile the estimates.
Department of Computer Engineering, VIIT, Pune-48

## Slide 33: Empirical Estimation Models
Department of Computer Engineering, VIIT, Pune-48

## Slide 34: Introduction
Estimation models for computer software use empirically derived formulas to predict effort as a function of LOC or FP
Resultant values computed for LOC or FP are entered into an estimation model
The empirical data for these models are derived from a limited sample of projects
  Consequently, the models should be adjusted to reflect local software development conditions
Department of Computer Engineering, VIIT, Pune-48

## Slide 35: COCOMO
Stands for COnstructive COst MOdel
Introduced by Barry Boehm in 1981 in his book “Software Engineering Economics”
Became one of the well-known and widely-used estimation models in the industry
It has evolved into a more comprehensive estimation model called COCOMO II
COCOMO II is actually a hierarchy of three estimation models
As with all estimation models, it requires sizing information and accepts it in three forms: object points, function points, and lines of source code
Department of Computer Engineering, VIIT, Pune-48

## Slide 36: COCOMO Models
Application composition model - Used during the early stages of software engineering when the following are important
  Prototyping of user interfaces
  Consideration of software and system interaction
  Assessment of performance
  Evaluation of technology maturity
Early design stage model – Used once requirements have been stabilized and basic software architecture has been established
Post-architecture stage model – Used during the construction of the software
Department of Computer Engineering, VIIT, Pune-48

## Slide 37: Stages of COCOMO
Basic COCOMO
Intermediate COCOMO
Complete/Detailed COCOMO
Department of Computer Engineering, VIIT, Pune-48

## Slide 38
The first level, Basic COCOMO can be used for quick and slightly rough calculations of Software Costs. Its accuracy is somewhat restricted due to the absence of sufficient factor considerations.
Intermediate COCOMO takes these Cost Drivers into account and Detailed COCOMO additionally accounts for the influence of individual project phases, i.e in case of Detailed it accounts for both these cost drivers and also calculations are performed phase wise henceforth producing a more accurate result.

## Slide 39: Basic COCOMO
Effort = a1 х (KLOC)a2 PM
Tdev = b1 x (Effort)b2 Months
KLOC- estimated size in Kilo Lines of Code
a1, a2, b1, b2 are constants for each category of software products
Tdev is the estimated time to develop the software, expressed in months,
Effort is the total effort required to develop the software product, expressed in person months (PMs).
Department of Computer Engineering, VIIT, Pune-48

## Slide 40: Estimation of development effort
The above formula is used for the cost estimation of for the basic COCOMO model, and also is used in the subsequent models. The constant values a,b,c and d for the Basic Model for the different categories of system:
For the three classes of software products, the formulas for estimating the effort based on the code size are shown below:
Organic : Effort = 2.4(KLOC)1.05 PM
Semi-detached : Effort = 3.0(KLOC)1.12 PM
Embedded : Effort = 3.6(KLOC)1.20 PM
Department of Computer Engineering, VIIT, Pune-48

## Slide 41: Estimation of development time
For the three classes of software products, the formulas for estimating the development time based on the effort are given below:
Organic : Tdev = 2.5(Effort)0.38 Months
Semi-detached : Tdev = 2.5(Effort)0.35 Months
Embedded : Tdev = 2.5(Effort)0.32 Months .
Department of Computer Engineering, VIIT, Pune-48

## Slide 42: Case Study
Assume that the size of an organic type software product has been estimated to be 32,000 lines of source code. Assume that the average salary of software engineers be Rs. 15,000/- per month. Determine the effort required to develop the software product and the nominal development time.
Department of Computer Engineering, VIIT, Pune-48

## Slide 43: Answer
From the basic COCOMO estimation formula for organic software:
Effort = 2.4 х (32)1.05 = 91 PM
Nominal development time = 2.5 х (91)0.38 = 14 months
Cost required to develop the product = 14 х 15,000 = Rs. 210,000/-
Department of Computer Engineering, VIIT, Pune-48

## Slide 44: Intermediate COCOMO Cost Drivers
Personnel Factors
  Applications experience
  Programming language experience
  Virtual machine experience
  Personnel capability
  Personnel experience
  Personnel continuity
  Platform experience
  Language and tool experience
Product Factors
  Required software reliability
  Database size
  Software product complexity
  Required reusability
  Documentation match to life cycle needs
  Product reliability and complexity
Department of Computer Engineering, VIIT, Pune-48

## Slide 45
COST DRIVERS | VERY LOW | LOW | NOMINAL | HIGH | VERY HIGH
Product Attributes |  |  |  |  | 
Required Software Reliability | 0.75 | 0.88 | 1.00 | 1.15 | 1.40
Size of Application Database |  | 0.94 | 1.00 | 1.08 | 1.16
Complexity of The Product | 0.70 | 0.85 | 1.00 | 1.15 | 1.30
Hardware Attributes |  |  |  |  | 
Runtime Performance Constraints |  |  | 1.00 | 1.11 | 1.30
Memory Constraints |  |  | 1.00 | 1.06 | 1.21
Volatility of the virtual machine environment |  | 0.87 | 1.00 | 1.15 | 1.30
Required turnabout time |  | 0.94 | 1.00 | 1.07 | 1.15

## Slide 46
Personnel attributes | VERY LOW | LOW | NOMINAL | HIGH | VERY HIGH
Analyst capability | 1.46 | 1.19 | 1.00 | 0.86 | 0.71
Applications experience | 1.29 | 1.13 | 1.00 | 0.91 | 0.82
Software engineer capability | 1.42 | 1.17 | 1.00 | 0.86 | 0.70
Virtual machine experience | 1.21 | 1.10 | 1.00 | 0.90 | 
Programming language experience | 1.14 | 1.07 | 1.00 | 0.95 | 
Project Attributes |  |  |  |  | 
Application of software engineering methods | 1.24 | 1.10 | 1.00 | 0.91 | 0.82
Use of software tools | 1.24 | 1.10 | 1.00 | 0.91 | 0.83
Required development schedule | 1.23 | 1.08 | 1.00 | 1.04 | 1.10

## Slide 47
The project manager is to rate these 15 different parameters for a particular project on a scale of one to three. Then, depending on these ratings, appropriate cost driver values are taken from the above table. These 15 values are then multiplied to calculate the EAF (Effort Adjustment Factor). The Intermediate COCOMO formula now takes the form:
E=(a(KLOC)b) * EAF

## Slide 48
SOFTWARE PROJECTS | A | B
Organic | 3.2 | 1.05
Semi Detached | 3.0 | 1.12
Embeddedc | 2.8 | 1.20
The values of a and b in case of the intermediate model are as follows:

## Slide 49: COCOMO Cost Drivers (continued)
Platform Factors
  Execution time constraint
  Main storage constraint
  Computer turn-around time
  Virtual machine volatility
  Platform volatility
  Platform difficulty
Project Factors
  Use of software tools
  Use of modern programming practices
  Required development schedule
  Classified security application
  Multi-site development
  Requirements volatility
Department of Computer Engineering, VIIT, Pune-48

## Slide 50: Complete COCOMO
Basic and intermediate COCOMO models consider a software product as a single homogeneous entity.
Most large systems are made up several smaller sub-systems.
These sub-systems may have widely different characteristics. For example, some sub-systems may be considered as organic type, some semidetached, and some embedded
Department of Computer Engineering, VIIT, Pune-48

## Slide 51: Complete COCOMO
Not only that the inherent development complexity of the subsystems but also for some subsystems the reliability requirements may be high, for some of the development team might have no previous experience of similar development, and so on.
The complete COCOMO model considers these differences in characteristics of the subsystems and estimates the effort and development time as the sum of the estimates for the individual subsystems.
The cost of each subsystem is estimated separately. This approach reduces the margin of error in the final estimate.
Department of Computer Engineering, VIIT, Pune-48

## Slide 52: Complete COCOMO
A distributed Management Information System (MIS) product for an organization having offices at several places across the country can have the following sub-components:
Database part
Graphical User Interface (GUI) part
Communication part
Department of Computer Engineering, VIIT, Pune-48

## Slide 53: Complete COCOMO
The communication part can be considered as embedded software. The database part could be semi-detached software, and the GUI part organic software. The costs for these three components can be estimated separately, and summed up to give the overall cost of the system.
Department of Computer Engineering, VIIT, Pune-48

## Slide 54: Complete/Detailed COCOMO
Detailed COCOMO incorporates all characteristics of the intermediate version with an assessment of the cost driver’s impact on each step of the software engineering process. The detailed model uses different effort multipliers for each cost driver attribute. In detailed cocomo, the whole software is divided into different modules and then we apply COCOMO in different modules to estimate effort and then sum the effort.
The Six phases of detailed COCOMO are:
Planning and requirements
System design
Detailed design
Module code and test
Integration and test
Cost Constructive model
The effort is calculated as a function of program size and a set of cost drivers are given according to each phase of the software lifecycle.

## Slide 55: Make/Buy Decision
It is often more cost effective to acquire rather than develop software
Managers have many acquisition options
  Software may be purchased (or licensed) off the shelf
  “Full-experience” or “partial-experience” software components may be acquired and integrated to meet specific needs
  Software may be custom built by an outside contractor to meet the purchaser’s specifications
The make/buy decision can be made based on the following conditions
  Will the software product be available sooner than internally developed software?
  Will the cost of acquisition plus the cost of customization be less than the cost of developing the software internally?
  Will the cost of outside support (e.g., a maintenance contract) be less than the cost of internal support?
Department of Computer Engineering, VIIT, Pune-48

## Slide 56: References
https://docs.google.com/presentation/d/1YOXcdiIMgiapHYVNcqSa1oo58kyvrhxZwV4h6sLW4DY/htmlpresent.
https://www.geeksforgeeks.org/software-engineering-cocomo-model/
Department of Computer Engineering, VIIT, Pune-48

## Slide 57
Thank You
Department of Computer Engineering, VIIT, Pune-48